## master thesis
A Visualization Tool for Code-to-Test Traceability: Timeline
Steps to Carry out | Tasks | Hours
Collect Java Files | 1. Write code to traverse the directory structure and collect .java files. 2.Implement basic error handling for file access. | 10
Parse Java Source Files | 1. Integrate JavaParser or a similar library into your project. 2. Write code to parse Java source files and extract class and method information. 3. Handle edge cases and errors in the source code gracefully. | 80
Extract Class and Method Information | 1. Design data structures to store class and method information. 2. Refine the parsing logic to extract relevant details accurately. 3. Handle inheritance and other complexities in Java classes. | 100
Collect Test Files | 1. Extend the file collection code to include test files. 2. Ensure the code is capable of distinguishing between source and test directories. | 10
Determine Dependencies | 1. Analyze test files to identify method dependencies. 2. Implement a mechanism to track dependencies between methods. 3. Handle cases where dependencies are across different classes. | 300
Generate HTML Output | 1. Design the HTML structure for displaying class and method information. 2. Implement logic to generate the HTML file with appropriate tooltips. 3. Ensure proper formatting and styling using HTML/CSS. | 100
Testing and Validation | 1. Develop a comprehensive set of test cases to validate the tool. 2. Test the tool with various Java projects of different sizes and complexities. 3. Debug and refine the tool based on test results. | 200
Documentation | 1. Create detailed documentation for installing and using the tool. 2. Include examples, screenshots, and explanations of the generated HTML output. 3. Document limitations, known issues, and potential future improvements. | 100
900